## Summary
Apollo Camera & Laser Network Configuration Summary
Updated on: 08-06-2026 12:04
Item | Status |  | Metric | Value
Intel X710 PCIe NIC driver installed | Completed |  | Configured cameras | 4 / 4
VLAN 10 and VLAN 20 PC NICs configured | Completed |  | Configured lasers | 2 / 3
Camera IP configuration verified | Completed |  | Successful ping tests | 6 / 6 completed devices
Laser IP configuration started | Partially Completed |  | Pending device | Sidewall 2 Laser
Completed Work
No. | Description
1 | Installed/updated Intel X710/X557-AT 10G PCIe network adapter drivers using Intel driver package.
2 | Configured PC NIC1 for VLAN 10 with static IPv4 192.168.1.10/24.
3 | Configured PC NIC2 for VLAN 20 with static IPv4 192.168.3.10/24.
4 | Configured and verified persistent IPs for all 4 Lucid cameras.
5 | Configured Tread Laser IP from old 192.168.6.20 range to final 192.168.1.23 and verified ping.
6 | Configured Sidewall 1 Laser IP from old 192.168.5.20 range to final 192.168.3.22 and verified ping.
7 | Sidewall 2 Laser is not connected now and will be configured later with final IP 192.168.3.24.
8 | Jumbo frame is configured on PC side; end-to-end jumbo verification is still pending on switch/camera path.
Camera Network | Completed | All four cameras visible in ArenaView and camera_check.py.
Current Status
Area | Status | Remarks
Camera Network | Completed | All four cameras visible in ArenaView and camera_check.py, ping OK.
Laser Network | Partially Completed | Tread Laser and Sidewall 1 Laser configured. Sidewall 2 Laser is pending/not connected.
Jumbo Frame | Pending verification | PC MTU is configured; switch/camera jumbo path still needs verification.

## Camera Mapping
Final Camera IP Mapping
Device Role | Model | Serial Number | VLAN | Switch Port | PC NIC Adapter | PC NIC IP | Camera IP | Subnet Mask | Gateway | DHCP | Persistent IP | LLA | Ping Status | Arena/Open Status | Final Status
Sidewall 1 Camera | TRT04KG-M | 254901432 | VLAN 10 | Port 9 | VLAN10_10G_PC_NIC1 | 192.168.1.10 | 192.168.1.21 | 255.255.255.0 | 0.0.0.0 | False | True | True | OK | Open Status OK | Completed
Inner Camera | TRI02KA-M | 254901428 | VLAN 10 | Port 10 | VLAN10_10G_PC_NIC1 | 192.168.1.10 | 192.168.1.22 | 255.255.255.0 | 0.0.0.0 | False | True | True | OK | Open Status OK | Completed
Sidewall 2 Camera | TRT04KG-M | 254901431 | VLAN 20 | Port 11 | VLAN20_10G_PC_NIC2 | 192.168.3.10 | 192.168.3.20 | 255.255.255.0 | 0.0.0.0 | False | True | True | OK | Open Status OK | Completed
Tread Camera | TRT04KG-M | 254901430 | VLAN 20 | Port 12 | VLAN20_10G_PC_NIC2 | 192.168.3.10 | 192.168.3.21 | 255.255.255.0 | 0.0.0.0 | False | True | True | OK | Open Status OK | Completed

## Laser Mapping
Final Laser IP Mapping and Status
Device Role | Device ID / Serial | Final IP | Subnet Mask | Gateway | VLAN | Switch Port | Status | Remarks
Tread Laser | M0006994 / MAC 00-01-0D-C8-59-23 | 192.168.1.23 | 255.255.255.0 | 0.0.0.0 | VLAN 10 | Port 13 | Completed | Configured in Network Configuration Tool and ping verified.
Sidewall 1 Laser | M0006674 / MAC 00-01-0D-C8-55-58 | 192.168.3.22 | 255.255.255.0 | 0.0.0.0 | VLAN 20 | Port 14 | Completed | Configured in Network Configuration Tool and ping verified.
Sidewall 2 Laser | Not connected | 192.168.3.24 | 255.255.255.0 | 0.0.0.0 | VLAN 20 | Port 15 | Pending | Not connected now. Will configure later.

## Network Setup
PC NIC and Switch Port Configuration
Component | Switch Port | VLAN | IP Address | Subnet Mask | Gateway | Speed/MTU | Status
PC NIC1 - VLAN10_10G_PC_NIC1 | Port 17 | VLAN 10 | 192.168.1.10 | 255.255.255.0 | Blank | 10 Gbps / MTU 9000 intended | Configured
PC NIC2 - VLAN20_10G_PC_NIC2 | Port 18 | VLAN 20 | 192.168.3.10 | 255.255.255.0 | Blank | 10 Gbps / MTU 9000 confirmed | Configured
Internet Adapter - Ethernet 7 | IT/Internet network | Corporate network | 10.65.117.x | 255.255.255.0 | 10.65.117.64 | Internet only | Do not modify
Notes
1 | Default gateway kept blank on camera NICs to avoid Windows routing conflicts.
2 | Internet remains on Ethernet 7; camera networks are isolated on VLAN 10 and VLAN 20.
3 | Jumbo Packet was set to 9014 on Intel X710 NIC. Windows MTU showed 9000 for VLAN20_10G_PC_NIC2.
4 | Jumbo frame end-to-end verification is pending because large ICMP ping above 1472 bytes did not pass.
5 | ArenaView auto-selected Device Stream Channel Packet Size around 7500 B during streaming test.
Laser Port Configuration
Component | Switch Port | VLAN | Final IP Address | Subnet Mask | Gateway | Status | Remarks
Tread Laser | Port 13 | VLAN 10 | 192.168.1.23 | 255.255.255.0 | 0.0.0.0 | Completed | Old IP range 192.168.6.x; ping verified after change.
Sidewall 1 Laser | Port 14 | VLAN 20 | 192.168.3.22 | 255.255.255.0 | 0.0.0.0 | Completed | Old IP range 192.168.5.x; ping verified after change.
Sidewall 2 Laser | Port 15 | VLAN 20 | 192.168.3.24 | 255.255.255.0 | 0.0.0.0 | Pending | Not connected now; will configure later.
Temporary IP Notes
Tread Laser access | VLAN10_10G_PC_NIC1 | Temporary IP | 192.168.6.10 | 255.255.255.0 |  | Used/Removed | Used to access old 192.168.6.20 range.
Sidewall 1 Laser access | VLAN20_10G_PC_NIC2 | Temporary IP | 192.168.5.10 | 255.255.255.0 |  | Used/Removed | Used to access old 192.168.5.20 range.

## Validation Tests
Camera Validation Test Results
Test Area | Device | IP | Status | Evidence/Notes | Date
Ping | Sidewall 1 Camera | 192.168.1.21 | PASS | Confirmed from terminal log | 2026-06-03 11:59
Ping | Inner Camera | 192.168.1.22 | PASS | Confirmed from terminal log | 2026-06-03 11:59
Ping | Sidewall 2 Camera | 192.168.3.20 | PASS | Confirmed from terminal log | 2026-06-03 11:59
Ping | Tread Camera | 192.168.3.21 | PASS | Confirmed from terminal log | 2026-06-03 11:59
Arena API | All Cameras | All final IPs | PASS | No duplicate serials found | 2026-06-03 11:59
Jumbo ICMP | Sidewall 2 Camera | 192.168.3.20 | PENDING | Switch/camera jumbo path verification required | 2026-06-03 11:59
Ping | Tread Laser | 192.168.1.23 | PASS | Confirmed after changing laser IP | 2026-06-08 12:04
Ping | Sidewall 1 Laser | 192.168.3.22 | PASS | Confirmed after changing laser IP | 2026-06-08 12:04
Connection | Sidewall 2 Laser | 192.168.3.24 | PENDING | Will configure later when connected | 2026-06-08 12:04
Tool | Network Configuration Tool | Laser devices | PASS | Sidewall 2 pending | 2026-06-08 12:04